## Data Inventory
ClearOffer — Data Inventory & Coverage Matrix
Tracks every data field sourced by ClearOffer: where it comes from, which markets are covered, what's missing, and known issues. Status: ✅ Live ⚡ In Sprint 🔒 Blocked ❌ Not sourced
Category | Data Field | Source / API | Status | BCC Brisbane | Moreton Bay | Gold Coast | Sunshine Coast | Sydney (NSW) | Melbourne (VIC) | Notes / Issues
PROPERTY IDENTITY
Property Identity | Geocoded address | Google Geocoding API | ✅ Live | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Google Places autocomplete + Geocoding. Strips ', Australia' suffix added by Places. National coverage.
Property Identity | Lot plan number (e.g. 15RP182797) | BCC DCDB — Property_boundaries_Parcel | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. BCC open data — combines BCC + QLD DCDB. Brisbane only. QLD DCDB available state-wide but separate service.
Property Identity | Lot area (m²) | BCC DCDB — Property_boundaries_Parcel | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. Confirmed returning 1086m² for 6 Glenheaton Court. Field: LOT_AREA. Brisbane only via BCC service.
Property Identity | Lot boundary polygon | BCC DCDB — Property_boundaries_Parcel | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. WGS84 polygon used to intersect all overlay layers. More accurate than point-in-polygon for large lots.
ZONING
Zoning | Zone code (e.g. LDR) | ZoneIQ → BCC City Plan | ✅ Live | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ZoneIQ ingests BCC, council ArcGIS, NSW ePlanning, VIC Vicmap. National coverage. Sprint 14 replaces BCC overlays with direct API but zoning remains via ZoneIQ.
Zoning | Zone name (e.g. Low Density Residential) | ZoneIQ → BCC City Plan | ✅ Live | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Same as zone code. ZoneIQ normalises zone names across councils.
FLOOD OVERLAYS
Flood | Creek/waterway flood planning area (FPA 1–5) | BCC City Plan open data (direct) | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. Direct call to services2.arcgis.com/dEKgZETqwmDAh1rP. Lot boundary polygon intersection returns ALL FPAs that touch the lot. Confirmed FPA4+FPA5 for 6 Glenheaton Court. Brisbane only.
Flood | Brisbane River flood planning area (FPA 1–5) | BCC City Plan open data (direct) | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. Separate layer for river flooding vs creek flooding. Both queried simultaneously.
Flood | Overland flow flood area | BCC Flood Awareness — Flood_Awareness_Overland_Flow | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 15. CONFIRMED: returns overland flow hit for 6 Glenheaton Court — the 'unmapped' flow the stormwater consultant found IS in this dataset. Previously missed entirely by ZoneIQ.
Flood | 1-in-100 year combined flood extent (1% AEP) | BCC Flood Awareness — 1pct_Annual_Chance | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 15. Standard planning risk benchmark. Confirmed hit for Carindale property.
Flood | Flooded in January 2011? | BCC Flood Awareness — Historic_Jan2011 | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 15. Major buyer concern — 2011 was Brisbane's worst flood since 1974. Result for 6 Glenheaton: NOT flooded. Important nuance for buyers.
Flood | Flooded in February 2022? | BCC Flood Awareness — Historic_Feb2022 | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 15. Most recent major flood event. Result for 6 Glenheaton: NOT flooded.
FIRE & ENVIRONMENT
Bushfire | Bushfire hazard area (High/Medium/Buffer) | BCC City Plan open data (direct) | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. BCC Bushfire_overlay service. Confirmed: Medium + High hazard buffer for Carindale (large lot near Minnippi Parklands). ZoneIQ showed 'buffer' — correct category but wrong source.
Biodiversity | Koala habitat area | BCC City Plan — Biodiversity_areas_overlay_Koala_habitat_areas | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 16. Confirmed hit for Carindale. Restricts vegetation clearing, triggers koala impact assessment for development.
Biodiversity | Biodiversity area (High ecological significance) | BCC City Plan — Biodiversity_areas_overlay_Biodiversity_areas | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 16. Confirmed hit for Carindale. Development may trigger ecological assessment.
HERITAGE & CHARACTER
Heritage | Heritage listed (yes/no) | BCC City Plan open data (direct) | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. BCC Heritage_overlay service. Confirmed not listed for Carindale.
Character | Traditional building character overlay | BCC City Plan — Traditional_building_character_overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. Strong design controls, demolition requires approval. Not applicable to Carindale.
Character | Dwelling house character overlay | BCC City Plan — Dwelling_house_character_overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 14. Confirmed hit for Carindale (6 Glenheaton Court). Design standards apply to extensions and new builds.
NOISE & AIRCRAFT
Aircraft Noise | ANEF noise contour (formal) | ZoneIQ → BCC City Plan ANEF layer | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | ANEF contours from BCC City Plan. Brisbane Airport only. Confirmed no ANEF overlay for Carindale — but operational flight paths DO affect this property. ANEF is structurally incomplete for operational noise.
Aircraft Noise | Operational flight path noise | Airservices WebTrak — NO API | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | CRITICAL GAP. No public API exists. WebTrak (webtrak.emsbk.com/bne3) is a browser tool only. Sprint 13 added WebTrak link as disclaimer. Steve is on Airservices noise engagement list for Brisbane — product cannot programmatically detect this.
SOIL & CONTAMINATION
Soil | Acid sulfate soils overlay | BCC City Plan — PotentialAndActual_acid_sulfate_soils_overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 16. Confirmed hit for Carindale. Affects excavation and construction — pool, footings, extensions all require ASS management plan.
Contamination | Contaminated land overlay | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | Service name not yet confirmed on BCC ArcGIS endpoint. Needs investigation. High value for ex-industrial sites.
INFRASTRUCTURE
Infrastructure | High voltage powerline (nearby, within 100m) | BCC City Plan — HV_powerline overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 20. LINE layer — queried via centroid + 100m buffer. Confirmed no hit for Carindale (correct).
Infrastructure | High voltage easement (on lot) | BCC City Plan — HV_easements overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 20. POLYGON layer. Confirmed no hit for Carindale.
Infrastructure | Petroleum pipeline easement | BCC City Plan — Petroleum_pipelines overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 20. POLYGON layer. Confirmed no hit for Carindale.
Infrastructure | Road hierarchy (arterial/local) | BCC City Plan — Roads_hierarchy_overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 19. LINE layer — centroid + 50m buffer. Auto-derives road type qualifier. Glenheaton Court returns local/residential (correct). Replaces manual buyer qualifier question.
WATERWAYS
Waterways | Waterway corridor overlay | BCC City Plan — Waterway_corridors_overlay_Waterway_corridors | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 19. Development setback/buffer zone along creeks and Brisbane River. Confirmed accessible (no hit for Carindale — correct, not near named waterway).
Waterways | Wetlands overlay | BCC City Plan — Wetlands_overlay | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 19. Confirmed accessible. No hit for Carindale.
SCHOOLS
Schools | Primary school catchment name | ZoneIQ → QLD DoE ingested data | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | ZoneIQ has ingested QLD DoE catchment polygons. Confirmed correct: Belmont SS for Carindale. Live API requires auth — ZoneIQ ingestion is correct approach.
Schools | Secondary school catchment name | ZoneIQ → QLD DoE ingested data | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Confirmed correct: Whites Hill State College for Carindale.
Schools | ICSEA score (socio-educational index) | MySchool / ACARA (annual ingest) | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 21. Live ACARA API or manually curated JSON. Currently null — ZoneIQ v2 dropped ICSEA. Annual data, changes rarely. Belmont SS: 1068, Whites Hill: 988.
SUBURB MARKET STATS
Suburb Stats | Suburb median house price | Static table in config.js (CoreLogic sourced) | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | 100 Brisbane suburbs manually entered. Will drift over time. PropTechData /suburbs/statistics replaces this when confirmed (Sprint 17).
Suburb Stats | Average days on market (DOM) | Static table in config.js | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Same static table. Same limitations.
Suburb Stats | 12-month price growth % | Static table in config.js | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Same static table.
Suburb Stats | 10-year CAGR % | Static table in config.js | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Same static table.
Suburb Stats | Clearance rate % | Static table in config.js | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Same static table.
Suburb Stats | Live suburb median (web search cross-check) | Claude web search → propertyvalue.com.au etc. | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Research pass in buyers-brief.js. Claude searches for current median before writing Brief. Confirmed finding $1.7M Carindale median. propertyvalue.com.au bot-blocks server fetch — only accessible via Claude web search.
Suburb Stats | Live suburb stats (all fields) | PropTechData /suburbs/statistics | 🔒 Blocked | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 17 — BLOCKED. Awaiting PropTechData terms confirmation (call Monday 13 April). Replaces entire static table with live data.
COMPARABLE SALES & AVM
Comparables | AVM estimate + range + confidence | Dev fixture (illustrative) / PropTechData | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Currently dev fixture (Sprint 12). Real AVM from PropTechData /properties/avm — BLOCKED. Fixture returns ~suburb median ±8%. Claude web search cross-validates.
Comparables | Comparable sales (address, price, date, config) | Dev fixture (illustrative) / PropTechData | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Dev fixture covers 10 Brisbane suburbs. Real data from PropTechData /market-activity/sales — BLOCKED pending VG licence + pricing confirmation. CRITICAL: fixture data must never appear in production.
Comparables | Suburb 10yr price timeseries | PropTechData /suburbs/timeseries | 🔒 Blocked | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 10 — BLOCKED. Planned for Brief 5-10yr outlook section.
LISTING DATA
Listing | Listed price | Domain developer API | 🔒 Blocked | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Sprint 22 — BLOCKED. Domain ticket #2899077 awaiting response. This is the most valuable missing field — affects verdict, valuation anchor, negotiation scripts. National coverage once approved.
Listing | Days on market (actual listing) | Domain developer API | 🔒 Blocked | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Sprint 22 — BLOCKED. Actual DOM for THIS listing, not suburb average. Critical for negotiation leverage calculation.
Listing | Beds / baths | Domain developer API | 🔒 Blocked | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Sprint 22 — BLOCKED. When available, removes need for buyer to look this up. Will auto-remove beds/baths qualifier question.
Listing | Agent name | Domain developer API | 🔒 Blocked | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Sprint 22 — BLOCKED. Useful context in Brief.
Listing | Property description / photos | Domain developer API | 🔒 Blocked | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Sprint 22 — BLOCKED. Could significantly improve valuation accuracy if beds/baths/features extracted from description.
BUYER QUALIFIERS (manual input)
Qualifier | Property condition (Original / Updated / Renovated) | Buyer input (inspection) | ✅ Live | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | Permanent qualifier — only the buyer knows this from physical inspection. Cannot be derived from data. Applied as ±5–15% valuation modifier.
Qualifier | Road type (Main road / Quiet street) | Buyer input → being replaced by BCC road hierarchy | ⚡ Sprint | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | Sprint 19 will auto-derive this from BCC road hierarchy layer and REMOVE this question for Brisbane properties. Will remain as manual fallback for non-Brisbane.
UNRESOLVED GAPS
Gap | Building age / construction year | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | No public API. BCC building approvals data exists but not queryable by address. Domain listing sometimes includes this. Currently absent.
Gap | Title type (freehold / leasehold / community title) | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | Queensland titles data (QLD Land Title Register) requires paid access via CITEC or similar. Not currently sourced.
Gap | Easements on title | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | Title search required — paid service. PropTechData or InfoTrack (email sent 10 April) may provide this. Critical for subdivision candidates.
Gap | Body corporate / strata (units) | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | No public API for body corporate levies or sinking fund. Significant for unit purchases. PropTechData may have.
Gap | Rental history / current tenancy | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | No public source. Relevant for investor buyers.
Gap | Landslide susceptibility | BCC City Plan — Landslide_overlay (tested: no hit for Brisbane flat suburbs) | ✅ Live | ✅ | ❌ | ❌ | ❌ | ❌ | ❌ | BCC Landslide_overlay confirmed accessible but returns no hit for Carindale (correct — flat suburb). Should be added to fetchBCCOverlays() — only relevant for hilly suburbs like Bardon, Paddington, Taringa.
Gap | Contaminated land (ex-industrial sites) | ❌ Not sourced | ❌ Not sourced | ❌ | ❌ | ❌ | ❌ | ❌ | ❌ | BCC has a contaminated land layer but exact service name not confirmed. Needs investigation on services2.arcgis.com.

## Legend & Coverage Plan
ClearOffer — Data Legend & Geographic Coverage Roadmap
Item | Description
STATUS
✅ Live | Currently deployed and returning data in production/dev
⚡ Sprint | Confirmed technically feasible, sprint written, building now or next
🔒 Blocked | Technically feasible but waiting on external approval or data access
❌ Not sourced | Not currently available — either no public API or not yet investigated
COVERAGE
✅ (green) | Confirmed working for this market
❌ (red) | Not available — different council, different data source needed
⚡ (blue) | In progress / planned
— (grey) | Not applicable
DATA SOURCES
BCC open data | services2.arcgis.com/dEKgZETqwmDAh1rP — 2,130 layers, free, no auth, Brisbane only
ZoneIQ | zoneiq-sigma.vercel.app — national coverage, pre-ingested. Being replaced for Brisbane overlays.
Google Geocoding/Places | Per-address geocoding and autocomplete. National.
PropTechData (Nexu) | api.nexu.com.au — AVM, comparables, suburb stats. BLOCKED pending terms.
Domain developer API | developer.domain.com.au — listing data. BLOCKED pending approval.
QLD DoE (schools) | Annual KML ingest — school catchment polygons. Auth required for live API.
MySchool / ACARA | Annual ICSEA scores. Script to ingest or manual curation.
Airservices WebTrak | NO API — browser tool only. Linked as disclaimer, cannot be programmatically queried.
Geographic Coverage Roadmap
MARKET | COVERAGE STATUS | DATA SOURCE | NOTES
BCC Brisbane | ✅ LIVE / In Sprint | BCC open data (services2.arcgis.com) | All overlays, cadastre, flood history. Best coverage of any market.
Moreton Bay (MBRC) | ❌ Not started | MBRC ArcGIS (separate council) | Different council, different ArcGIS endpoint. ZoneIQ has zones. Overlays need investigation.
Gold Coast (GCCC) | ❌ Not started | GCCC ArcGIS (separate council) | ZoneIQ has zones. GCCC has open data portal. Flood + bushfire overlays available but not yet wired.
Sunshine Coast (SCRC) | ❌ Not started | SCRC ArcGIS | ZoneIQ has zones. Less urban density — lower priority.
Sydney (NSW) | ❌ Not started | NSW ePlanning ArcGIS | ZoneIQ has zones via NSW ePlanning. Flood data from councils (complex — 33 LGAs). Heritage via NSW Heritage Office.
Melbourne (VIC) | ❌ Not started | VIC Vicmap Planning | ZoneIQ has zones via Vicmap. VIC overlays have different structure — flood from individual councils. Heritage via VIC Heritage Register.
National (all markets) | 🔒 Partial via ZoneIQ | ZoneIQ zones only | ZoneIQ provides zoning for 84 councils nationally. Overlays, flood, heritage all require council-specific work beyond zones.